## Project Plan
© 2023. Prachi Jain. All rights reserved.
Milestone | Task | Explanation | Responsibility | Dependency | Duration | Start Date | End Date | Comment | Sprint 1 |  | Sprint 2 |  | Sprint 3 |  | Sprint 4 |  | Sprint 5 |  | Sprint 6 |  | Sprint 7 |  | Sprint 8
[9 empty] | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16
User Research | Identify Target Audience | Define the specific group of potential customers who are most likely to use the e-commerce platform. | Market Researcher |  | 2 | bar: Week 1
| Conduct Market Analysis | Study the current market trends, competitors, and customer preferences to identify opportunities. | Market Researcher | Identify Target Audience | 8 | bar: Week 1 to Week 2
| User Surveys and Interviews | Gather insights from potential users through surveys and interviews to understand their needs. | Market Researcher | Conduct Market Analysis | 15 | bar: Week 1 to Week 3
| Analyze Competitor Websites | Evaluate competitors' websites to identify best practices, gaps, and potential areas of improvement. | Market Researcher |  | 10 | bar: Week 2 to Week 3
| Define User Personas | Create fictional representations of target customers to better understand their motivations and goals. | Market Researcher |  | 5 | bar: Week 4
| Usability Testing By External Stakeholders | Test the e-commerce platform with real users to identify usability issues and gather feedback. | Market Researcher |  | 10 | bar: Week 9 to Week 10
| Card Sorting or Information Architecture | Organize website content to ensure intuitive navigation and smooth user experience. | Market Researcher |  | 8 | bar: Week 9 to Week 10
| A/B Testing | Conduct experiments to compare different design or content variations for optimization. | Market Researcher |  | 12 | bar: Week 10 to Week 11
| Mobile User Research | Study user behavior and preferences on mobile devices to optimize the mobile e-commerce experience. | Market Researcher |  | 12 | bar: Week 11 to Week 12
| Eye-Tracking Studies | Use eye-tracking technology to understand what users pay attention to and improve page layouts. | Market Researcher |  | 15 | bar: Week 12 to Week 14
| Scroll and Click Heatmaps | Analyze user interactions on the website using heatmaps to improve page design and layout. | Market Researcher |  | 7 | bar: Week 15 to Week 16
| Conversion Funnel Analysis | Identify potential drop-off points in the user journey and optimize the conversion funnel. | Market Researcher |  | 10 | bar: Week 15 to Week 16
Product Management | Market Research and Analysis | Conduct research on target market, competitors, trends, and customer needs to identify opportunities and make data-driven product decisions. | Product Manager |  | 8 | bar: Week 1 to Week 2
| Define Product Vision and Strategy | Develop a clear vision and long-term strategy for the e-commerce product to align with business goals and customer expectations. | Product Manager |  | 2 | bar: Week 1
| Create Product Roadmap | Plan and prioritize product development initiatives, features, and improvements to guide the product's growth and evolution. | Product Manager |  | 3 | bar: Week 2
| User Persona Development | Identify and understand the target audience by creating user personas, ensuring product decisions cater to their specific needs. | Product Manager |  | 2 | bar: Week 2
| Requirements Gathering and Analysis | Collaborate with stakeholders to gather and analyze product requirements, ensuring they are well-defined and feasible for development. | Product Manager |  | 10 | bar: Week 2 to Week 3
| Competitive Analysis | Continuously monitor competitors' offerings, strengths, and weaknesses to maintain a competitive edge and identify areas for improvement. | Product Manager |  | 5 | bar: Week 4
| Stakeholder Communication | Regularly communicate product updates, progress, and plans to internal teams and stakeholders to maintain alignment and support. | Product Manager |  | Ongoing | bar: Week 5 to Week 16
| Feature Prioritization | Prioritize product features based on business value, user needs, and development effort to maximize the product's impact. | Product Manager |  | 7
| Product Documentation | Create and maintain product documentation, including user guides, feature specifications, and release notes for internal and external use. | Product Manager |  | Ongoing | bar: Week 5 to Week 16
| Coordinate Product Development | Collaborate with cross-functional teams (designers, developers, QA) to ensure timely and successful product development and releases. | Product Manager |  | Ongoing | bar: Week 5 to Week 16
| User Acceptance Testing (UAT) | Engage with users to conduct UAT, gather feedback, and ensure the product meets quality standards and user expectations. | Product Manager |  | 5 | bar: Week 9
| Pricing and Monetization Strategy | Develop pricing models and strategies to optimize revenue generation and align with the value provided by the e-commerce product. | Product Manager |  | 7 | bar: Week 1
| Customer Support and Feedback Analysis | Gather customer feedback and support data to identify pain points and opportunities for product improvements and customer satisfaction. | Product Manager |  | Ongoing | bar: Week 9 to Week 16
| Performance Monitoring and KPI Tracking | Define key performance indicators (KPIs) for the e-commerce product and regularly monitor and analyze metrics for continuous improvement. | Product Manager |  | Ongoing | bar: Week 9 to Week 16
| Product Training and Education | Conduct internal training sessions to educate teams about the product's features, benefits, and value proposition. | Product Manager |  | 5 | bar: Week 9
| End-of-Life Planning | Evaluate and plan for the product's end-of-life, including migration strategies or sunsetting the product, when necessary. | Product Manager |  | 7
UX UI | User Research and Analysis | Conduct user research to understand target audience, behavior, needs, and pain points to inform the design process. | UX UI Designer |  | 5 | bar: Week 1
| Information Architecture | Plan the website's structure, navigation, and content organization to create an intuitive and user-friendly e-commerce experience. | UX UI Designer | Requirements Gathering and Analysis | 5 | bar: Week 2
| Wireframing and Prototyping | Create low-fidelity wireframes and interactive prototypes to visualize the layout and flow of key pages before finalizing the design. | UX UI Designer | Requirements Gathering and Analysis | 14 | bar: Week 3 to Week 4
| Mobile Responsive Design | Ensure the e-commerce website's design is responsive and optimized for various devices, providing a seamless user experience. | UX UI Designer |  | 7 | bar: Week 5
| Visual Design and Branding | Develop the visual design elements, including color schemes, typography, and branding, to establish a consistent and appealing look. | UX UI Designer |  | 14 | bar: Week 5 to Week 6
| Checkout Process Optimization | Optimize the checkout process to reduce friction, enhance usability, and improve conversion rates for a smooth user journey. | UX UI Designer |  | 10 | bar: Week 6 to Week 7
| Product Page Design | Design visually engaging and informative product pages, showcasing products with clear images, descriptions, and call-to-action. | UX UI Designer |  | 7 | bar: Week 7 to Week 8
| Category and Navigation Design | Create intuitive category pages and navigation menus to help users find products quickly and easily. | UX UI Designer |  | 7 | bar: Week 8 to Week 9
| Interactive Element Design | Design interactive elements like buttons, forms, and product galleries to engage users and encourage action. | UX UI Designer |  | 7 | bar: Week 9 to Week 10
| A/B Testing and User Feedback Incorporation | Collaborate with the UX team to conduct A/B tests and incorporate user feedback into design iterations for continuous improvement. | UX UI Designer |  | Ongoing | bar: Week 9 to Week 16
| Accessibility and Inclusivity Considerations | Ensure the e-commerce website's design meets accessibility standards, making it usable for all users, including those with disabilities. | UX UI Designer |  | 10 | bar: Week 3 to Week 4
| Performance Optimization | Optimize graphics and design elements to improve website loading speed and performance for a better user experience. | UX UI Designer |  | 5 | bar: Week 16
| Error and Validation Message Design | Design clear and user-friendly error messages and validation prompts to guide users during form submissions and error scenarios. | UX UI Designer |  | 5 | bar: Week 16
| Collaborate with Developers and QA | Work closely with development and QA teams to ensure the design is implemented accurately and meets quality standards. | UX UI Designer |  | Ongoing | bar: Week 5 to Week 16
| User Onboarding and Tutorials | Design onboarding experiences and tutorials to help new users navigate and understand the e-commerce platform. | UX UI Designer |  | 7 | bar: Week 13 to Week 14
| Design System Development | Create a design system and style guide to maintain consistency and streamline the design process for future updates and features. | UX UI Designer |  | 14 | bar: Week 14 to Week 16
Platform | Defining the platform architecture of the application | Deciding the architecture for an ecommerce site for scalability, robust, availability, maintainability, reusability, usability, security, accessibility. | Solution Architects | Requirements Gathering and Analysis | 8 days | bar: Week 3 to Week 4
| Infrastructure Setup | Provision and configure the necessary infrastructure for the ecommerce platform, including servers, databases, load balancers, and content delivery networks (CDNs). | Platform Engineers |  | 3 days | bar: Week 4
| Scalability Planning | Develop a strategy to ensure the platform can handle increasing traffic and data as the business grows. This may involve horizontal and vertical scaling, caching mechanisms, and resource monitoring. | Platform Engineers |  | 5 days | bar: Week 3 to Week 4
| High Availability Setup | Implement measures to ensure the ecommerce platform remains available and operational even during hardware or network failures. This may include redundancy, failover systems, and load balancing. | Platform Engineers |  | 4 days | bar: Week 3 to Week 4
| Security Implementation | Harden the platform's security by applying best practices, setting up firewalls, encrypting data in transit and at rest, and implementing authentication and authorization mechanisms to protect user data and prevent unauthorized access. | Platform Engineers |  | 6 days | bar: Week 7 to Week 8
| Backup and Disaster Recovery | Set up regular data backups and create a disaster recovery plan to ensure data integrity and availability in the event of a system failure or data loss. | Platform Engineers |  | 4 days | bar: Week 8
| Continuous Integration and Deployment | Establish an automated CI/CD pipeline to facilitate seamless code integration, testing, and deployment. This reduces manual errors, speeds up development cycles, and ensures new features are rolled out efficiently and reliably. | Platform Engineers |  | 6 days | bar: Week 5
| Monitoring and Logging Setup | Implement monitoring tools and logging mechanisms to track the platform's performance, identify bottlenecks or issues, and proactively address potential problems to maintain optimal system health. | Platform Engineers |  | 4 days | bar: Week 6
| Database Optimization | Optimize database performance, indexing, and query execution to ensure fast and efficient data retrieval and storage. This improves overall platform responsiveness and user experience. | Platform Engineers |  | 5 days | bar: Week 7
| API Development and Management | Design and develop APIs that facilitate communication between different components of the ecommerce platform, as well as with third-party services or external partners. Ensure proper documentation and versioning for ease of integration. | Platform Engineers |  | 6 days | bar: Week 16
| Content Management System Setup | Integrate a content management system (CMS) to allow easy management and updating of website content, product catalogs, and other dynamic elements. | Platform Engineers |  | 3 days | bar: Week 15
| Payment Gateway Integration | Integrate with various payment gateways to enable secure and seamless payment processing for customer transactions. Ensure compliance with PCI DSS standards for handling cardholder data securely. | Platform Engineers |  | 5 days | bar: Week 7
| Shipping and Logistics Integration | Integrate with shipping and logistics providers to automate shipping processes, calculate shipping costs, and provide real-time tracking information to customers. | Platform Engineers |  | 4 days
| Personalization and Recommendation Systems | Implement personalized user experiences through recommendation systems based on user behavior and historical data. Utilize machine learning algorithms to offer product recommendations tailored to individual users. | Platform Engineers |  | 6 days
Software Development | Frontend Architecture and Tech Stack Finalization | Deciding the architecture for an ecommerce site for scalability, robust, availability, maintainability, reusability, usability, security, accessibility. | Solution Architects | Requirements Gathering and Analysis | 8 days | bar: Week 3 to Week 4
| Backend Architecture and Tech Stack Finalization | Deciding the architecture for an ecommerce site for scalability, robust, availability, maintainability, reusability, usability, security, accessibility. | Solution Architects | Requirements Gathering and Analysis | 8 days | bar: Week 3 to Week 4
| User Authentication - Login Page | Create user account systems with secure authentication, password management, and account settings. | Frontend Engineers |  | 3 | bar: Week 5
| User Authentication - User Database Integration | Create user account systems with secure authentication, password management, and account settings. | Backend Engineers |  | 3 | bar: Week 5
| Product Catalog - Display Product List | Display a list of products available for purchase. | Frontend Engineers |  | 4 | bar: Week 6
| Product Catalog - Database Setup and API | Display a list of products available for purchase. | Backend Engineers |  | 4 | bar: Week 6
| Product Details Page - UI Design | Provide detailed information about a specific product. | Frontend Engineers |  | 4 | bar: Week 7
| Product Details Page - Product Data Integration | Provide detailed information about a specific product. | Backend Engineers |  | 4 | bar: Week 7
| Shopping Cart - Cart UI and Functionality | Enable users to add, remove, and manage items to buy. | Frontend Engineers |  | 5 | bar: Week 8
| Shopping Cart - Cart Management Backend | Enable users to add, remove, and manage items to buy. | Backend Engineers |  | 5 | bar: Week 8
| Payment Processing - Payment Gateway UI and Integration | Handle secure payment transactions for orders. | Frontend Engineers |  | 7 | bar: Week 8
| Payment Processing - Payment Processing Backend | Handle secure payment transactions for orders. | Backend Engineers |  | 7 | bar: Week 8
| Checkout Process - Checkout UI and Flow | Guide users through the payment and order confirmation. | Frontend Engineers |  | 6 | bar: Week 9
| Checkout Process - Payment Gateway Integration | Guide users through the payment and order confirmation. | Backend Engineers |  | 6 | bar: Week 9
| User Profiles - Profile Page | Allow users to manage their profiles and preferences. | Frontend Engineers |  | 3 | bar: Week 10
| User Profiles - User Data Management | Allow users to manage their profiles and preferences. | Backend Engineers |  | 3 | bar: Week 10
| Search Functionality - Search UI and Filtering | Enable users to search and filter products efficiently. | Frontend Engineers |  | 4 | bar: Week 11
| Search Functionality - Search Algorithm Integration | Enable users to search and filter products efficiently. | Backend Engineers |  | 4 | bar: Week 11
| Order History - Order History Page | Display the history of past orders for each user. | Frontend Engineers |  | 4 | bar: Week 12
| Order History - Order Data Management | Display the history of past orders for each user. | Backend Engineers |  | 4 | bar: Week 12
| Ratings and Reviews - Review Submission Form | Let users submit and view product reviews and ratings. | Frontend Engineers |  | 4 | bar: Week 13
| Ratings and Reviews - Review Data Management | Let users submit and view product reviews and ratings. | Backend Engineers |  | 4 | bar: Week 13
| Wishlist - Wishlist UI and Functionality | Allow users to create and manage a list of desired items. | Frontend Engineers |  | 5 | bar: Week 14
| Wishlist - Wishlist Data Management | Allow users to create and manage a list of desired items. | Backend Engineers |  | 5 | bar: Week 14
| Product Recommendations - Recommendation Algorithm Integration | Suggest relevant products based on user behavior. | Frontend Engineers |  | 8 | bar: Week 15 to Week 16
| Product Recommendations - User Behavior Tracking | Suggest relevant products based on user behavior. | Backend Engineers |  | 8 | bar: Week 15 to Week 16
| Order Management - Order Tracking and Status | Manage and track orders from placement to delivery. | Frontend Engineers |  | 8
| Order Management - Order Data Management | Manage and track orders from placement to delivery. | Backend Engineers |  | 8
| Inventory Management - Inventory Tracking and Alerts | Monitor and update product stock levels. | Frontend Engineers |  | 6
| Inventory Management - Inventory Database Integration | Monitor and update product stock levels. | Backend Engineers |  | 6
| Admin Dashboard - Admin UI for Site Management | Provide an interface for website management. | Frontend Engineers |  | 4
| Admin Dashboard - Admin Backend Functionality | Provide an interface for website management. | Backend Engineers |  | 4
| Customer Support - Support Chat UI and Integration | Offer chat support and manage support tickets. | Frontend Engineers |  | 5
| Customer Support - Support Ticket Management Backend | Offer chat support and manage support tickets. | Backend Engineers |  | 5
| Analytics and Reporting - Data Visualization Integration | Track website data and present it in a visual format. | Frontend Engineers |  | 7
| Analytics and Reporting - Data Processing and Storage | Track website data and present it in a visual format. | Backend Engineers |  | 7
| Email Notifications - Email Templates and Delivery | Send automatic email notifications to users. | Frontend Engineers |  | 4
| Email Notifications - Email Service Integration | Send automatic email notifications to users. | Backend Engineers |  | 4
| SEO Optimization - Metadata and URL Structuring | Optimize the website for better search engine ranking. | Frontend Engineers |  | 3
| SEO Optimization - SEO Backend Integration | Optimize the website for better search engine ranking. | Backend Engineers |  | 3
| Performance Optimization - Page Speed and Load Time Improvement | Improve website speed and performance. | Frontend Engineers |  | 3
| Performance Optimization - Backend Performance Tuning | Improve website speed and performance. | Backend Engineers |  | 3
| Security Measures - XSS and CSRF Protection | Implement measures to safeguard against attacks. | Frontend Engineers |  | 3
| Security Measures - Backend Security Configuration | Implement measures to safeguard against attacks. | Backend Engineers |  | 3
| Mobile Responsiveness - Mobile UI Design and Development | Ensure the website works well on mobile devices. | Frontend Engineers |  | 4
| Mobile Responsiveness - Mobile Backend Adaptation | Ensure the website works well on mobile devices. | Backend Engineers |  | 4
| Social Media Integration - Social Media Sharing Buttons | Enable users to share products on social media. | Frontend Engineers |  | 3
| Social Media Integration - Social Media API Integration | Enable users to share products on social media. | Backend Engineers |  | 3
| Multilingual Support - Language Selection UI | Provide the website in multiple languages. | Frontend Engineers |  | 6
| Multilingual Support - Language Data Management | Provide the website in multiple languages. | Backend Engineers |  | 6
| GDPR Compliance - Cookie Consent Banner | Ensure compliance with data protection regulations. | Frontend Engineers |  | 4
| GDPR Compliance - User Data Handling Compliance | Ensure compliance with data protection regulations. | Backend Engineers |  | 4
QA | Functional Testing | Verifies if all the features and functionalities of the e-commerce site are working as expected and meet the specified requirements. It ensures that the website functions properly for users. | Automation Testers | Feature Development | Ongoing | bar: Week 5 to Week 16
| Usability Testing | Focuses on evaluating the user experience and usability aspects of the e-commerce site. It assesses how easy it is for users to navigate, interact, and perform tasks on the website. | Automation Testers | Feature Development | Ongoing | bar: Week 5 to Week 16
| Performance Testing | Tests the website's performance under different conditions, such as load testing, stress testing, and scalability testing, to ensure it can handle the expected user traffic without issues. | Manual Testers | Feature Development | Ongoing | bar: Week 5 to Week 16
| Security Testing | Identifies and addresses vulnerabilities and weaknesses in the e-commerce site's security measures to protect sensitive user information, financial transactions, and prevent cyber-attacks. | Manual Testers | Feature Development | Ongoing | bar: Week 5 to Week 16
| Compatibility Testing | Ensures that the e-commerce site works seamlessly across various devices, browsers, and operating systems to provide a consistent user experience to a diverse range of users. | Manual Testers | Feature Development | Ongoing | bar: Week 5 to Week 16
| Mobile Testing | Specifically focuses on testing the e-commerce site's functionality, usability, and performance on mobile devices to cater to the growing number of mobile users and their unique needs. | Manual Testers | Feature Development | Ongoing | bar: Week 5 to Week 16
| Payment Gateway Testing | Validates the integration and functionality of payment gateways, ensuring smooth and secure payment processing for users during the checkout process. | Manual Testers | Feature Development | Ongoing | bar: Week 9 to Week 16
| Load Testing | Evaluates how the e-commerce site performs under different user loads to assess its capacity and response time, ensuring it can handle peak traffic and provide a smooth user experience. | Manual Testers | Feature Development | Ongoing | bar: Week 5 to Week 16
| Regression Testing | Verifies that new changes or updates do not adversely impact the existing functionalities of the e-commerce site, ensuring a stable and error-free user experience after updates. | Automation Testers | Feature Development | Ongoing | bar: Week 5 to Week 16
| Cross-Browser Testing | Checks the compatibility and consistency of the e-commerce site's appearance and functionality across various web browsers to ensure a uniform experience for all users. | Automation Testers | Feature Development | Ongoing | bar: Week 5 to Week 16
Performance Marketing | Define Marketing Strategy and Objectives | Develop a comprehensive performance marketing strategy aligned with business goals, targeting audience segments and defining key performance indicators. | Performance Marketer |  | 14 | bar: Week 1 to Week 3
| Conduct Market Research and Competitor Analysis | Analyze the market landscape, consumer behavior, and competitor strategies to identify opportunities and gain a competitive edge. | Performance Marketer |  | 10 | bar: Week 2 to Week 3
| Plan and Execute Paid Advertising Campaigns | Manage the implementation of paid campaigns across platforms such as Google Ads, Facebook, Instagram, and other relevant channels. | Performance Marketer |  | 21 | bar: Week 9 to Week 12
| Search Engine Optimization (SEO) | Optimize website content, meta tags, and structure to improve organic search visibility and attract relevant traffic from search engines. | Performance Marketer | Development of First Stable Version of the Application | Ongoing | bar: Week 7 to Week 8
| Performance Tracking and Analytics | Set up and monitor performance metrics, analyzing campaign data and customer behavior to make data-driven decisions and optimize marketing efforts. | Performance Marketer |  | Ongoing | bar: Week 10 to Week 16
| Budget Management and ROI Analysis | Monitor marketing budgets, allocate resources effectively, and evaluate the return on investment (ROI) for various marketing campaigns. | Performance Marketer |  | Ongoing | bar: Week 10 to Week 16
| Email Marketing and Automation | Develop and execute email marketing campaigns, including automated flows and personalized messages to engage and retain customers. | Performance Marketer |  | 14 | bar: Week 16
| Influencer Marketing | Collaborate with influencers and industry partners to drive brand awareness and leverage their reach to target relevant audiences. | Performance Marketer |  | 14 | bar: Week 16
| Social Media Management and Advertising | Manage and optimize social media platforms, running targeted ads, and engaging with followers to foster brand loyalty and generate leads. | Performance Marketer |  | 21
| Content Marketing and Blogging | Develop content marketing strategies, create valuable blog posts, and other content to attract and engage potential customers. | Performance Marketer |  | 14
| Conversion Rate Optimization (CRO) | Analyze website data, conduct A/B tests, and implement changes to improve the conversion rate of visitors into customers. | Performance Marketer |  | 21
| Affiliate Marketing | Establish and manage affiliate partnerships to drive traffic and sales through affiliate marketing programs. | Performance Marketer |  | 14
| Remarketing and Retargeting | Set up retargeting campaigns to re-engage website visitors who haven't converted and encourage them to return and make a purchase. | Performance Marketer |  | 14
| Customer Segmentation and Personalization | Implement strategies to segment customers and deliver personalized marketing messages based on their preferences and behavior. | Performance Marketer |  | 14
| Loyalty Programs and Customer Retention | Design and execute loyalty programs and initiatives to retain existing customers and encourage repeat purchases. | Performance Marketer |  | 14
| Collaborate with Creative and Design Teams | Work with creative teams to produce marketing collateral, graphics, and ad creatives that align with the brand's messaging and aesthetics. | Performance Marketer |  | Ongoing
| Monitor and Respond to Online Reviews and Feedback | Monitor customer reviews and feedback on various platforms and respond appropriately to maintain a positive brand reputation. | Performance Marketer |  | Ongoing